## ProductBacklog
Product Backlog ID | Source | Priority (M/S/C/W) | User Story ID | User Story Name | User | Scrum Team Assigned | Complexity | Risk/ Impact | Type
This column is used to uniquely identify each row on this worksheet. User Stories in a given Sprint are traced back to the Product Backlog using the User Story ID to the details on the Sprint Backlog Product Backlog ID | This column documents the source from which the expanded requirement came (e.g., statement of work, change request, work session, standards document etc.). Source | Column to prioritize requirements using MoSCoW) - Must Have, Should Have, Could Have, Won't Have Priority (M/S/C/W) | Column for uniquely identifying the use case, Originates from Use case Model [RA.023] When used Corresponds to a use case number on the Use Case Catalog sheet. Note - Requirements satisfied by COTS applications that are defined in SOW are assigned a use case in order to create traceability. Not required for requirements satisfied by the COTS App that are not in SOW. User Story ID | Brief description of the requirements necessary to fulfill the objective User Story Name | Column used to identify owner of requirement as defined by SOW and/or supporting documentation. Defined assumptions are treated as requirements owned by designated party. User | Column used to identify owner of requirement as defined by SOW and/or supporting documentation. Defined assumptions are treated as requirements owned by designated party. Scrum Team Assigned | Complexity of the functional requirement. Very Simple Simple Average Complex Very Complex Complexity | Technical, Organizational, External project risk associated with the requirement. This is further detailed in the Project Risk Management Plan. What is the probability that something will go wrong in meeting the requirement? A risk might happen, or it might not; there is some uncertainty. Use H (High), M (Medium), L (Low). Risk/ Impact | Defines whether the User Story is Functional, Non-Functional or Technical type. Type | This column is used to link the User Story to the User Acceptance test scenarios that validate the requirement was satisfied. User Acceptance Test Case ID | This column is used to provide supporting information, such as changes to the original requirement. Comments | fdasf fdaf
1 | Standard document | High | PECUNIABANK:001 | Design Documentation for Backend application | Ganesh | Ganesh | Average | Low | Non-Functional | Design is fullfilled agaist Business requirement
2 | Standard document | High | PECUNIABANK:002 | Bootstraping the project | Ganesh | Ganesh | Low |  | Non-Functional | Checking Against the Application Setup and ensure the equired dependencies and run the main code and check the server is tarted without errors
3 | Standard document |  | PECUNIABANK:003 | Account | Ganesh | Ganesh |  | High | Functional | Designing the user cases against Business requirement
4 | Standard document | High | PECUNIABANK:004 | Transaction | Ganesh | Ganesh | Complex | Low | Functional | Designing the user cases against Business requirement
5 | Standard document | High | PECUNIABANK:005 | Loan | Ganesh | Ganesh | Complex | High | Functional | Designing the user cases against Business requirement
6 | Standard document | High | PECUNIABANK:006 | Passbook | Ganesh | Ganesh | Complex | High | Functional | Designing the user cases against Business requirement
| Work session | High | PECUNIABANK:007 | Populating test data in database | Ganesh | Ganesh | Simple |  | Non-Functional
7 | Work session | High | PECUNIABANK:008 | Testing all the functionalities in postman whether all are working or not | Ganesh | Ganesh | Complex | High | Non-Functional
10
11
12
13
14
15
Sprint 2
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41

## Rakesh
Product Backlog ID | User Story ID | User Story Task Step Number | Task Step Description |  | Assigned Date | Original Estimated Time | Adjustment Estimate | Status
1 | PEC_BANK:01 | 1 | Test Cases Template |  | 2020-08-03 | 1 hr | 2 hrs | Completed
|  | 2 | Product Backlog Sheet |  | 2020-08-03 | 1 hr | 1.5 hrs | Completed
|  | 3 | Sprint plan sheet |  | 2020-08-03 | 1 hrs | 0.5 hrs | Completed
|  | 4 | Entity Class Diagram |  | 2020-08-04 | 1.5 hrs
|  | 5 | Use Case Diagram |  | 2020-08-04 | 1 hr
|  | 6 | Sequence Diagram |  | 2020-08-04 | 1 hr
2 | PEC_BANK:02 | 7 | Creating a Spring boot starter project |  |  | 0.5 hr
|  | 8 | Adding dependencies in Pom.xml and initializing it |  |  | 1 hr
|  | 9 | Adding server, jpa and logging properties in application.properties |  |  | 1 hr
3 | PEC_BANK:03 | 10 | ADD ACCOUNT | DAO LAYER |  | 3 hrs
|  |  |  | SERVICE LAYER |  | 3 hrs
|  |  |  | ENTITY LAYER |  | 3 hrs
|  |  |  | SERVICE IMPLEMENTATION LAYER |  | 3 hrs
4 | PEC_BANK:04 | 11 | UPDATE ACCOUNT | DAO LAYER |  | 3 hrs
|  |  |  | SERVICE LAYER |  | 3 hrs
|  |  |  | SERVICE IMPLEMENTATION LAYER |  | 3 hrs
5 | PEC_BANK:05 | 12 | DELETE ACCOUNT | DAO LAYER |  | 3 hrs
|  |  |  | SERVICE LAYER |  | 2 hrs
|  |  |  | SERVICE IMPLEMENTATION LAYER |  | 2 hrs

## Lova Raju
Product Backlog ID | User Story ID | User Story Task Step Number | Task Step Description | Assigned Date | Original Estimate | Adjustment Estimate | Status | Actual Effort
1 | PECUNIABANK_01 | 1 | Test case Template | 2020-08-03 | 1.5 hrs |  | Completed
|  | 2 | Product Backlog | 2020-08-03 | 1 hr |  | Completed
|  | 3 | Sprint Plan Sheet | 2020-08-03 | 1 hr
|  | 4 | Entity Class Design |  | 2 hrs
|  | 5 | Use Case Diagram |  | 1.5 hrs
|  | 6 | Sequence Diagram |  | 1.5 hrs
2 | PECUNIABANK_02 | 1 | Creating a Spring boot starter project |  | .5hr | .5hr
|  | 2 | Adding dependencies in Pom.xml and initializing it |  | 1 hr | 1hr
|  | 3 | Adding server, jpa and logging properties in application.properties |  | 1 hr | 1hrs
3 | PECUNIABANK_03 | 1 | CREDIT TRANSACTIONS; DAO |  | 3 hrs | 0.5 hrs
|  | 2 | CREDIT TRANSACTIONS; SERVICE |  | 3 hrs | 0,5 hrs
|  | 3 | CREDIT TRANSACTIONS; CONTROLLER |  | 3 hrs | 0,5 hrs
4 | PECUNIABANK_04 | 1 | Populating the test data in database |  | 3 hr | 0.5 hrs
5 | PECUNIABANK_05 | 1 | Testing the functionalites in postman |  | 2 hrs | 1hr

## Venkata Sai
Product Backlog ID | User Story ID | User Story Task Step Number | Task Step Description |  | Assigned Date | Original Estimate | Adjustment Estimate | Status | Actual Effort
1 | PECUNIA BANK:001 | 1 | Test Cases Template |  | 2020-08-03 | 2 hrs | 1 hrs | completed
|  | 2 | Product Backlog Sheet |  | 2020-08-03 | 1 hrs | 0.5 hrs | completed
|  | 3 | Sprint plan sheet |  | 2020-08-03 | 1 hrs | 0.5 hrs | completed
|  | 4 | Entity Class Diagram |  | 2020-08-04 | 2 hrs
|  | 5 | Use Case Diagram |  | 2020-08-04 | 2 hrs
|  | 6 | Sequence Diagram |  | 2020-08-04 | 2 hrs
2 | PECUNIA BANK:002 | 1 | Creating a Spring boot starter project |  |  | 1hrs | 0.5 hrs
|  | 2 | Adding dependencies in Pom.xml and initializing it |  |  | 1 hrs | 0.5 hrs
|  | 3 | Adding server, jpa and logging properties in application.properties |  |  | 1 hrs | 0.5 hrs
3 | PECUNIA BANK:003 | 1 | PassBook Update | DAO |  | 3 hrs | 1.5 hrs
|  |  |  | SERVICE |  | 3 hrs | 1.5 hrs
|  |  |  | CONTROLLER |  | 3 hrs | 1.5 hrs
|  | 2 | Account Summary | DAO |  | 3 hrs | 1.5 hrs
|  |  |  | SERVICE |  | 3 hrs | 1.5 hrs
|  |  |  | CONTROLLER |  | 3 hrs | 1.5 hrs
4 | PECUNIA BANK:004 | 1 | Populating the test data in database |  |  | 3 hrs | 1hr
5 | PECUNIA BANK:005 | 1 | Testing the functionalites in postman | DAO,SERVICE,CONTROLLER |  | 2 hrs

## Satyam
Product Backlog ID | User Story ID | User Story Task Step Number | Task Step Description | Assigned Date | Original Estimate | Adjustment Estimate | Status | Actual Effort
1 | PECUNIABANK_01 | 1 | Test case Template | 2020-08-04 | 1.5 hrs |  | Completed
|  | 2 | Product Backlog | 2020-08-04 | 1 hr |  | Completed
|  | 3 | Sprint Plan Sheet | 2020-08-04 | 1 hr
|  | 4 | Entity Class Design |  | 2 hrs
|  | 5 | Use Case Diagram |  | 1.5 hrs
|  | 6 | Sequence Diagram |  | 1.5 hrs
2 | PECUNIABANK_02 | 1 | Creating a Spring boot starter project |  | .5hr | .5hr
|  | 2 | Adding dependencies in Pom.xml and initializing it |  | 1 hr | 1hr
|  | 3 | Adding server, jpa and logging properties in application.properties |  | 1 hr | 1hrs
3 | PECUNIABANK_03 | 1 | DEBIT TRANSACTIONS; DAO |  | 3 hrs | 0.5 hrs
|  | 2 | DEBIT TRANSACTIONS; SERVICE |  | 3 hrs | 0,5 hrs
|  | 3 | DEBIT TRANSACTIONS; CONTROLLER |  | 3 hrs | 0,5 hrs
4 | PECUNIABANK_04 | 1 | Populating the test data in database |  | 3 hr | 0.5 hrs
5 | PECUNIABANK_05 | 1 | Testing the functionalites in postman |  | 2 hrs | 1hr

## Sumanth
Product Backlog ID | User Story ID | User Story Task Step Number | Task Step Description |  | Assigned Date | Original Estimate | Adjustment Estimate | Status | Actual Effort
1 | PECUNIABANK:001 | 1 | Entity Class Design |  |  | 2 hrs | 1 hr
|  | 2 | Use case diagram |  |  | 1hr | 0.5 hr
|  | 3 | Sequence Diagram |  |  | 1hr | 0.5hr
|  | 4 | Class Layer diagram |  |  | 2 hrs | 1 hr
|  | 5 | Class Diagram |  |  | 2 hrs
|  | 6 | TestCaseTemplate |  |  | 2 hrs | 1hr | Completed | 2hrs
2 | PECUNIABANK:002 | 1 | Creating a Spring boot starter project |  |  | 1 hr | 0.5 hrs
|  | 2 | Adding dependencies in Pom.xml and initializing it |  |  | 1 hrs | 0,5 hrs
|  | 3 | Adding server, jpa and logging properties in application.properties |  |  | 1 hrs | 0,5 hrs
3 | PECUNIABANK:005 | 1 | Loan Request | DAO |  | 3 hrs | 1.5 hrs
|  |  |  | SERVICE |  | 3 hrs | 1.5 hrs
|  |  |  | CONTROLLER |  | 3 hrs | 1.5 hrs
|  | 2 | Loan Disbursal | DAO |  | 3 hrs | 1.5 hrs
|  |  |  | SERVICE |  | 3 hrs | 1.5 hrs
|  |  |  | CONTROLLER |  | 3 hrs | 1.5 hrs
4 | PECUNIABANK:007 | 1 | Populating the test data in database |  |  | 3 hrs | 1 hr
5 | PECUNIABANK:008 | 1 | Testing the functionalites in postman | DAO, SERVICE, CONTROLLER